## Start here
Speaker Briefing and Run of Show Kit
Free tool by Karl Lillrud, AI keynote speaker ¦ www.karllillrud.com
How to use
1. Speaker brief | Fill in one copy per speaker and send it at least 6 weeks before the event. A good brief is the difference between a tailored session and a stock talk.
2. Run of show | Enter the start time and durations. All start and end times recalculate when you move or change a slot.
3. Countdown plan | Enter your event date once. Every task gets a due date and shows how many days are left.
4. AV and stage | Agree this checklist with your production company and the speaker in the tech call.
5. Speaker budget | List every cost and every funding source. The sheet shows your funding gap.
Legend | Cells with a light yellow fill are for your input. Everything else calculates. The example rows show the expected format; overwrite them.
Tip | Save a copy per event. Next year you start from last year's file, not from zero.
Need a keynote? | Karl Lillrud speaks on AI, leadership and commerce. Fee guide and availability: www.karllillrud.com/organizers ¦ me@karllillrud.com

## Speaker brief
Speaker brief
One per speaker. Send 6 weeks before. Yellow cells are yours to fill in.
Section | Question | Your answer | Why the speaker needs it
Event | Event name, date, city and venue | Nordic Retail Summit, 12 March, Stockholm, Waterfront Congress Centre | Context and logistics
Event | Why does this event exist? (one sentence) |  | So the session serves your objective, not the speaker's
Event | Theme or tagline |  | Lets the speaker use your language
Audience | How many people, which roles and seniority? |  | Depth, examples and tone
Audience | What do they already know about the topic? |  | Avoids too basic or too advanced
Audience | What keeps them up at night right now? |  | Makes the session feel written for them
Audience | Mood and context (growth, cost cuts, merger, reorganization) |  | Avoids landmines
Session | Title and format (keynote, fireside, panel, workshop)
Session | Length, including Q&A
Session | The one thing the audience must leave with |  | The most important line in the brief
Session | Topics, words or companies to avoid
Session | What do the speakers before and after cover? |  | Prevents overlap, enables callbacks
Session | Can you share 2 or 3 company or industry examples to use? |  | Tailoring that the audience notices
Logistics | Arrival time, rehearsal slot, tech check
Logistics | Stage, screens, microphones, clicker, confidence monitor |  | See the AV and stage tab
Logistics | Recording and streaming: yes or no, and rights |  | Must be agreed in the contract
Logistics | Travel, hotel and transfers booked by whom?
Contacts | Main contact on the day (name, mobile)
Contacts | Who introduces the speaker? Send the intro text
Deadlines | Slides due, bio and photo due, promotional video due

## Run of show
Run of show
Enter the first start time in C5 and the durations in column D. Times recalculate automatically.
Event date | 2027-03-12
# | Item | Start | Duration (min) | End | On stage | AV and light cue | Owner | Notes
1 | Doors open, registration and coffee | 8:30 | 45 | 9:15 |  | Walk-in music, holding slide | Registration lead
2 | Welcome and housekeeping | 9:15 | 10 | 9:25 | MC | Stage wash, MC mic live | MC
3 | Opening keynote | 9:25 | 45 | 10:10 | Keynote speaker | Walk-on music, headset live, slides from speaker laptop | Stage manager
4 | Q&A with keynote speaker | 10:10 | 10 | 10:20 | MC and speaker | Two handheld runners | MC
5 | Coffee break and networking | 10:20 | 30 | 10:50 |  | Break slide with sponsor logos | Venue
6 | Panel discussion | 10:50 | 40 | 11:30 | Moderator and 3 panelists | 4 handhelds, chairs set | Stage manager
7 | Lunch | 11:30 | 60 | 12:30 |  | Break slide | Venue
8 | Breakout sessions | 12:30 | 50 | 13:20 | Workshop leads | Room AV per breakout | Room hosts
9 | Afternoon keynote | 13:20 | 40 | 14:00 | Speaker | Walk-on music, lavalier | Stage manager
10 | Closing remarks and survey QR | 14:00 | 10 | 14:10 | Host | Survey QR slide | MC
11 | Reception | 14:10 | 90 | 15:40 |  | Music, lights at 60 percent | Venue
12
13
14
15
16
17
18
19
20
21
22
23
24
25
| Total programme (minutes) |  | 430
| Programme ends at |  | 15:40

## Countdown plan
Countdown plan
Enter the event date in B3. Due dates and days left update automatically.
Event date | 2027-03-12 |  | Today | 2026-10-22
Days before (-) / after (+) | Task | Due date | Days left | Owner | Status | Notes
-120 | Agree objective, 3 measurable outcomes and budget | 2026-11-12 | 21 |  | Not started
-110 | Shortlist keynote speakers, send briefs and ask for proposals | 2026-11-22 | 31 |  | Not started
-100 | Book keynote speaker, sign agreement incl. recording rights | 2026-12-02 | 41 |  | Not started
-95 | Send sponsor proposals for keynote and stage | 2026-12-07 | 46 |  | Not started
-90 | Confirm venue, AV supplier and catering | 2026-12-12 | 51 |  | Not started
-85 | Collect speaker bio, photo and promotional video | 2026-12-17 | 56 |  | Not started
-80 | Launch event page and early bird tickets | 2026-12-22 | 61 |  | Not started
-70 | Publish speaker announcement and first social posts | 2027-01-01 | 71 |  | Not started
-60 | Detailed speaker brief call (15 to 30 minutes) | 2027-01-11 | 81 |  | Not started
-56 | Confirm speaker travel and hotel | 2027-01-15 | 85 |  | Not started
-45 | Early bird ends, start main campaign | 2027-01-26 | 96 |  | Not started
-40 | Draft run of show and stage plan | 2027-01-31 | 101 |  | Not started
-35 | Accessibility, dietary and special needs plan | 2027-02-05 | 106 |  | Not started
-30 | Confirm sponsors' deliverables and logos | 2027-02-10 | 111 |  | Not started
-28 | Write survey and impact measures | 2027-02-12 | 113 |  | Not started
-21 | Tech call with speaker and AV, agree slides format | 2027-02-19 | 120 |  | Not started
-14 | Final run of show to all crew and speakers | 2027-02-26 | 127 |  | Not started
-14 | Send know-before-you-go email | 2027-02-26 | 127 |  | Not started
-7 | Receive final slides, test video and sound | 2027-03-05 | 134 |  | Not started
-7 | Staff and volunteer briefing pack | 2027-03-05 | 134 |  | Not started
-3 | Print signage, badges and MC script | 2027-03-09 | 138 |  | Not started
-1 | Rehearsal and tech check on stage | 2027-03-11 | 140 |  | Not started
0 | Event day: survey QR on screen in the closing | 2027-03-12 | 141 |  | Not started
0 | Collect quotes and photos with permission | 2027-03-12 | 141 |  | Not started
1 | Send thank you and survey to attendees | 2027-03-13 | 142 |  | Not started
2 | Thank speakers, ask for testimonial and referrals | 2027-03-14 | 143 |  | Not started
7 | Send recordings and slides | 2027-03-19 | 148 |  | Not started
10 | Sponsor recap with numbers | 2027-03-22 | 151 |  | Not started
14 | One page results report to leadership | 2027-03-26 | 155 |  | Not started
30 | 30 day follow-up survey on actions taken | 2027-04-11 | 171 |  | Not started
Formulas:
Due date = B3+[Days before (-) / after (+)]

## AV and stage
AV and stage checklist
Agree in the tech call. Mark each line OK, Missing or Not needed.
Area | Item | Status | Notes
Audio | Wireless headset microphone for the keynote speaker | Open
Audio | Lavalier or handheld backup, fresh batteries | Open
Audio | Handheld microphones for Q&A, with runners | Open
Audio | Walk-on and walk-off music, approved and cued | Open
Video | Screen ratio agreed (16:9) and slides tested on the real screen | Open
Video | HDMI or USB-C to the speaker's laptop, or slides on the show computer | Open
Video | Video playback with sound from the slides tested | Open
Video | Confidence monitor facing the stage | Open
Video | Wireless clicker and a spare | Open
Light | Stage light on the speaker's face, no dark spots at the front edge | Open
Light | House lights at a level where the speaker can see the audience | Open
Stage | Water on stage, small table or stand | Open
Stage | Stage steps lit and taped, clear walk-on route | Open
Stage | Countdown clock visible to the speaker | Open
Recording | Recording rights agreed in writing | Open
Recording | Multi-camera recording with clean audio feed | Open
Recording | Speaker receives a copy of the full recording | Open
Streaming | Stream tested end to end, backup connection | Open
Virtual | Test call 2 to 5 days before, producer on standby | Open
People | Stage manager briefed, timing signals agreed (5 and 1 minute) | Open
| Items still open or missing | 20

## Speaker budget
Speaker budget and funding
Costs on the left, funding on the right. Example values show the format: replace them with your own.
Cost item | Quantity | Unit cost (EUR) | Total (EUR) | Funding source | Amount (EUR)
Keynote speaker fee | 1 | 30000 | 30000 | Presenting partner (sponsor) | 20000
Flights (business class) | 2 | 1400 | 2800 | Existing event budget | 10000
Hotel nights | 2 | 280 | 560 | Ticket uplift (VIP seats, extra tickets) | 4000
Ground transfers | 2 | 90 | 180 | Other | 0
AV and recording for the keynote | 1 | 3500 | 3500
Speaker gifts, books for attendees | 0 | 25 | 0
Other | 0 | 0 | 0
Total cost |  |  | 37040
Total funding |  |  | 34000
Funding gap (negative = covered) |  |  | 3040
Attendees |  |  | 300
Speaker cost per attendee |  |  | 123.4667
No budget for the speaker you want? The free Speaker Budget Playbook shows three ways to fund it: www.karllillrud.com/speaker-budget-playbook